## Graphical Overview
Acieta Project Milestones Overview
1st Day of Current Year | 2015-01-01 |  |  |  | 209.7143
Updated: | 2019-01-22 | [52 empty] | Clear |  | Set Colors
[6 empty] | Sold Hrs | [10 empty] | Budget Hrs | [10 empty] | Backlog | [10 empty] | Cmpltd Hrs
[52 empty] | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241
Job Number | PM | ME | EE | Tech | Customer | Total Sold Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Budget Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Backlog Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Cmptld Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Instsll | Rework | Over budget | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2655 | Steve Cooprider | Mark Poling | Bob Foulk | Ryan Smallfoot | Bobcat Gwinner Axle Cell | 0 | [45 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2505 | Greg Morehouse | Bryan Carsrud | Brad Bowhay | Ryan Smallfoot | New Hudson Facades Glass Loading Cells | 7767.7 | 983 | 1759 | 111.7 | 581 | 940 | 668 | 416 | 1189 | 0 | 1120 | 6667.7 | 983 | 759 | 111.7 | 581 | 940 | 668 | 416 | 1089 | 0 | 1120 | 5417 | 801 | 246 | 60 | 150 | 400 | 920 | 500 | 1120 | 0 | 1220 | 1171.11 | 182 | 843.5 | 57 | 15.17 | 25.7 | 0 | 0 | 46.24 | 0 | 1.5 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2627 | Steve Cooprider | Bryan Carsrud | Brad Bowhay | Ryan Smallfoot | Viking Pump Rotor L/UL | 0 | [45 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2627 | Steve Cooprider | Bryan Carsrud | Brad Bowhay | Ryan Smallfoot | Viking Pump Rotor L/UL | 0 | [45 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[5 empty] | Totals | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Manufacturing Outsourced | [51 empty] | 216 216: Action Items & Followup; 229 229: Signed Off From Last Report
[11 empty] | Mach / Fab Priorities | [40 empty] | 213 213: Mech Engineering; 214 214: ME; 216 216: 1.; 217 217: 2397 ET-MN PTT, on hold; 229 229: 1.
[11 empty] | 1 | [40 empty] | 213 213: Elec Engineering; 214 214: EE; 216 216: 2.; 217 217: 2398 TMCO, on hold; 229 229: 2.
[55 empty] | Fabrication / Manufacturing | M |  | 3. | 2452 Parker pallets versus tubs, review EOAT | [11 empty] | 3.
[11 empty] | 2 | [40 empty] | 213 213: Assembly / Wiring; 214 214: A; 216 216: 4.; 217 217: 2466 Metalex, eng approval & cycletime; 229 229: 4.
[55 empty] | Programming | P |  | 5. | 2476 Bobcat, robot only ordered | [11 empty] | 5.
[11 empty] | 3 | [40 empty] | 213 213: Runoff; 214 214: R; 216 216: 6.; 217 217: 2483 Altamont, (3) robots ordered; 229 229: New Purchase Orders
[55 empty] | Installation @ Channel | CI |  | 7. | 2484 Altamont, robot oinly ordered | [11 empty] | 1. | SA0782 Fabtech 2015, show is 11/9 thru 11/12
[11 empty] | 4 | [40 empty] | 213 213: Installation @ Customer; 214 214: I; 216 216: 8.; 229 229: 2.; 230 230: 2483 Altamont, (3) robots ordered
[58 empty] | 9. | [12 empty] | 3. | 2484 Altamont, robot oinly ordered
[11 empty] | 5 | [40 empty] | 216 216: 10.; 229 229: 4.
[58 empty] | 11. | [12 empty] | 5.
[11 empty] | 6 | [40 empty] | 216 216: 12.; 229 229: 6.
Active Documentation Projects and Issues(Updated 04-04-2016)
[11 empty] | 7 | [40 empty] | 216 216: Job #; 218 218: Customer; 226 226: Integration; 229 229: Installation; 232 232: Redlines; 236 236: OP Manual; 238 238: Signoff
[74 empty] | Mech |  | Elec.
Assembly Priorities
[11 empty] | 1 | [40 empty] | 216 216: 2481; 218 218: General Grind; 229 229: Bill Bailey; 236 236: No; 238 238: No
2
3
4
5
6
7
Teardown/Ship Priorities
1
2
6

## Data
ID | n/a-1 | Project_Manager_s__c | Mechanical_Engineer__c | Electrical_Engineer_s__c | LB__c | Controls__c | Robot_Tech_Programmers__c | n/a-2 | n/a-3 | Tracking__c | ME_Release__c | EE_Release__c | MFG_Complete__c | Finishing_Complete__c | Assembly_Complete__c | Run_Off_Internal__c | Run_Off_Acieta__c | Ship_Date_Notes__c | Integ_CP_End__c | Integr_CS_Start__c | Integ_CS_End__c | Documents_Done__c | Comments_Opps__c | n/a-4 | Customer_Visit__c | Operation result | Updated IDs | Date Time |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Acieta Project Milestones Overview - Updated: 1/22/2019 | [10 empty] | Current Project Milestones | [20 empty] | Sold Hours | [10 empty] | Target/Budgeted Hours | [10 empty] | Backlog Hours | [10 empty] | Actual Hours
SFID # | Job # | PM | ME | EE | LB | Controls | Int Team | Customer Project | Last Week | On Track | ME Release | EE Release | Manufacturing Complete | Finishing Complete | Assembly Complete | Internal Runoff | Customer Runoff | Ship Date | Channel Partner Install Complete | Install Start | Install Complete | Documentation Complete | Comments | Last Updated | Customer Visit | Mechanical Engineering Open Issues | Last Updated | Electrical Engineering Open Issues | Last Updated | Controls Status | Last Updated | Total Sold Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Budget Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Backlog Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Actual Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Rework | Over budget
a1b0G000007XJdDQAW | 2485 | Greg Morehouse | Bryan Carsrud | Brad Bowhay | N/A | PLC | Ryan Smallfoot | New Hudson Facades Structural & Weather Sealant Cells | Hold | Hold | [12 empty] | ON HOLD | 2017-05-08 | [7 empty] | 4760 | 858 | 339 | 162 | 86 | 108 | 347 | 417 | 1583 | 0 | 860 | 4794 | 727 | 339 | 162 | 86 | 273 | 347 | 417 | 1583 | 0 | 860 | 1056 | 110 | 97 | 9 | 0 | 0 | 50 | 0 | 100 | 0 | 690 | 3551.02 | 454.5 | 435 | 172 | 186.74 | 289.67 | 381.6 | 54.6 | 1111.08 | 0 | 396.75 | 69.08
a1b0G000007XJdXQAW | 2505 | Greg Morehouse | Bryan Carsrud | Brad Bowhay | Mithlo | PLC | Ryan Smallfoot | New Hudson Facades Glass Loading Cells | Hold | Hold | [12 empty] | ON HOLD | 2017-03-27 | [7 empty] | 7767.7 | 983 | 1759 | 111.7 | 581 | 940 | 668 | 416 | 1189 | 0 | 1120 | 6667.7 | 983 | 759 | 111.7 | 581 | 940 | 668 | 416 | 1089 | 0 | 1120 | 5417 | 801 | 246 | 60 | 150 | 400 | 920 | 500 | 1120 | 0 | 1220 | 1171.11 | 182 | 843.5 | 57 | 15.17 | 25.7 | 0 | 0 | 46.24 | 0 | 1.5 | 0
a1b0G000007XJe5QAG | 2539 | Travis Pinkelman | Shane Halverson | Brad Bowhay | Anderson |  | Dan Mitchell | 3M Valley Large Lens | Y | Y | [12 empty] | Closing the project in January | 2019-01-22
a1b0G000007XJeAQAW | 2544 | Travis Pinkelman | Rusell Ridgway | Bob Foulk | Mithlo | HMI | Andy Wiese | Gardner Denver CMM Addition | Y | Y | [9 empty] | TBD | TBD |  | This will not be considered until combo cell is completed first | 2019-01-22
a1b0G000007j8a3QAA | 2595 | Travis Pinkelman | Rusell Ridgway | Brad Bowhay | N/A | HMI | Ryan Smallfoot | Industrial Fab RIBS Cell | Y | Y | [12 empty] | Invoiced for T&E | 2019-01-22
a1b0G000007jagnQAA | 2600 | Travis Pinkelman | Mark Poling | Bob Foulk | Kilburn | HMI | Dan Mitchell | FMC/Ellison Bent Part LUL | Y | Y | [11 empty] | 2019-01-25 |  | 2019-01-22
a1b0G000007k7JhQAI | 2603 | Steve Cooprider | Bryan Carsrud | Bob Foulk | Anderson | HMI | Andy Wiese | PMC Saw Cut-Off and Pack Out | Y | Y | [9 empty] | 1/22/2019 (Glen - contractor) | 2019-01-29 |  | Glen scheduled to return late January. Jordan has designed the modification to the blowoff and we will send those parts to be installed when Glen returns. | 2019-01-18
a1b0G00000720LcQAI | 2605 | Travis Pinkelman | N/A | N/A | N/A | Mark P | Dan Mitchell | BD Diagnostics PLC Re-write | N | W | [10 empty] | 2019-02-01 |  | Sylas O'Neal is at BD this week. | 2019-01-22
a1b0G0000090VSkQAM | 2614 | Joseph Splichal | Robert Knox | Bob Foulk | Anderson | PLC | Andy Wiese | ConAgra Foods Palletizer | N | W | [10 empty] | 2019-02-01 | 2019-03-01 |  | 2019-01-21
a1b0G0000090vEVQAY | 2619 | Travis Pinkelman | Shane Halverson | Brad Bowhay | Kilburn | Burr | Ryan Smallfoot | Lennox RIBS2 | Y | Y | [7 empty] | 2019-02-20 |  | 2019-02-25 | 2019-03-22 |  | RW training 1/14/19; Lennox to program cell 1/28/19-2/15/19 | 2019-01-22 | 1/28/19-2/15/19
a1b0G0000091LKNQA2 | 2624 | Greg Morehouse | Ryan Tweedt | Bob Foulk | Anderson | HMI | Dan Mitchell | RMH / Landmark Snacks Case Packing | W | W | [10 empty] | 2019-01-25 | 2019-02-22 | New cups are installed and in production, wear improvement still TBD. RMH designing and building catch trays. | 2019-01-04
a1b0G0000091V8zQAE | 2625 | Travis Pinkelman, Jeff Boyer | Shane Halverson | Brad Bowhay | Kilburn | Burr | Andy Wiese, Ryan Smallfoot | Blue Bird RIBS x3 | W | W | [10 empty] | 2019-02-15 |  | Moved date out as all 3 cells should be completed by 2/1/19. Then we will have training. | 2019-01-22
a1b0G0000091tx3QAA | 2627 | Steve Cooprider | Bryan Carsrud | Brad Bowhay | Kilburn | HMI | Ryan Smallfoot | Viking Pump Rotor L/UL | Y | Y | [11 empty] | 2019-01-25 | Vince to return one last time to fix an issue with the L rotors. Mostly a logic issue | 2019-01-18
a1b0G0000091xAfQAI | 2628 | Travis Pinkelman | Shane Halverson | Brad Bowhay | Kilburn | Oscar | Ryan Smallfoot | RC Industries RIBS3 | Y | Y | [11 empty] | 2019-01-22 | Close by the end of January. Just ordered new cups for EOATs that was being used for tread material | 2019-01-22 |  |  |  | released 9-28-16 | 2016-09-28
a1b0G000009240VQAQ | 2629 | Steve Cooprider | Nick Cowell |  | Anderson |  | Andy Wiese | John Deere 2382 Modifications | Y | Y | [9 empty] | 2019-04-15 | 2019-04-19 |  | John Deere looking to determine if they have an additional robot that can be modified instead of taking down the line for the whole week. | 2019-01-18
a1b0G00000927u1QAA | 2630 | Steve Cooprider | Rusell Ridgway | Bob Foulk | Kilburn | HMI | Dan Mitchell | Micronutrients Palletizer | Y | W | [10 empty] | TBD |  | Customer still having issues with bagging system and will need to get the air out of the bags before we can do run-off and proceed with training. | 2019-01-18
a1b0G0000092LV6QAM | 2632 | Greg Morehouse | Ryan Tweedt | Bob Foulk | Kilburn | HMI | Dan Mitchell | RMH / Crosswinds 7 Bone Packaging | N | W | [5 empty] | TBD | TBD | TBD |  | TBD | TBD | TBD | RMH/Stone finished work on conveyor equipment week of 12/17; we are resgarting the integration work. New gripper has been tested but not at full speed; Dan working on it again starting 1/2/19. | 2019-01-03 | 1/5/2019 for customer runoff
a1b0G0000092VioQAE | 2633 | Joseph Splichal | Shane Halverson | Bob Foulk | Kilburn | Gerry | Ryan Smallfoot | Spartan Light Metal DCM 19 | Y | Y | [10 empty] | 2019-02-15 | 2019-03-15 | Return 1/28 | 2019-01-21 |  |  |  | released 09/06/16 | 2016-09-06
a1b0G0000092k2rQAA | 2635 | Steve Cooprider | Bryan Carsrud | Bob Foulk | Anderson | Oscar Gerry | Andy Wiese | Toyota Racing Development Integrex I-200 Mazak Cell | Y | Y | [10 empty] | 2019-03-08 |  | Bill to be there Monday morning, followed by Gerry on Wednesday. | 2019-01-18
a1b0G00000BfinXQAR | 2638 | Joseph Splichal |  | Bob Foulk | Anderson | HMI | Dan Mitchell | CapStone Autoviri 5.2 - Qty 20 | Y | Y | [7 empty] | 3 left to ship. | [5 empty] | 2019-01-21
a1b0G00000Bg64FQAR | 2644 | Travis Pinkelman | Shane Halverson | Bowhay & Schneckloth | Anderson | PLC | Ryan Smallfoot | Saginaw RIBS | W | W | [5 empty] | 2019-01-29 | 2019-02-05 | 2019-02-13 |  | 2019-02-18 | 2019-05-10 |  | Extending schedule 3 weeks | 2019-01-22 |  |  |  | released 10-5-16 | 2016-10-07
a1b0G00000C1nB1QAJ | 2645 | Travis Pinkelman | Bryan Carsrud | Bowhay & Schneckloth | Anderson | HMI | Dan Mitchell | Altitude Machine Tending | W | N | [9 empty] | TBD | TBD |  | Hartwig got release to ship the cell. After talking with Mark Sumner on Friday, I plan on working with WI on finding someone to possibly go install the cell | 2019-01-22
a1b0G00000C1jciQAB | 2646 | Steve Cooprider | Bryan Carsrud | Brad Bowhay | Kilburn | HMI | Dan Mitchell | Corning Gasket Dispense | Y | Y | [12 empty] | Phase 1 has finished. Phase 2 is still TBD - depending upon Corning's need for a primer application robot. A 30 day test will begin, and we may not know until mid-January. | 2019-01-18
a1b0G00000CKdZ1QAL | 2650 | Jeff Boyer | Bryan Carsrud | Darin Schneckloth | Anderson | HMI | Dan Mitchell | Bridgestone Gripper Design and Build | W | N | [5 empty] | 2019-01-21 | 2019-01-24 | 2019-01-31 |  | 2019-02-01 | 2019-02-22 | 2019-03-23 | Full system including gripper design and build. Rebuilt schedule on 8/9 and pushed dates 1 week based on late engineering release. New Schedule as of 8-14. Mgmt schedule review 8/29. 1-3-19 update...New runoff and delivery dates. 1-21-19....Project delayed due to vision issues finding ply materials on splice table.(1-22-19)
a1b0G00000CLMUIQA5 | 2654 | Steve Cooprider | Shane Halverson | Brad Bowhay | Anderson | N/A | Dan Mitchell | Bobcat Gwinner Frame Forming Cell | Y | Y |  |  |  |  | 2019-01-31 |  |  | 2019-02-06 |  |  |  |  | Assembly consists of kitting parts, completing electrical enclosures and op stations. Then testing the conveyors. | 2019-01-18
a1b0G00000CLRAiQAP | 2655 | Steve Cooprider | Mark Poling | Bob Foulk | Anderson | HMI | Ryan Smallfoot | Bobcat Gwinner Axle Cell | Y | Y | [10 empty] | End of February |  | Eddie now planning to work over the holiday weeks. Jeremy S. to start in January after Micronutrients, through February. | 2019-01-18
a1b0G00000CMSZuQAP | 2657 | Jeff Boyer | Nick Cowell | Bob Foulk | Anderson | N/A | Andy Wiese | 39702 Bobcat Bismarck BBF End Plate Welding Cell (Priority 3) | Y | Y | [11 empty] | 2019-02-01 | New schedule as of 7/11. New Schedule as of 8-14. New schedule as of 9/4
a1b0G00000CMSadQAH | 2660 | Jeff Boyer | Nick Cowell | Bob Foulk | Anderson | N/A | Andy Wiese | 39704-A Bobcat Bismarck BBF Bobtach Lg Weld Cell (Priority 2) | Y | Y | [11 empty] | 2019-02-01 | New schedule as of 7/11. New Schedule as of 8-14. New schedule as of 9/4
a1b0G00000CMSanQAH | 2661 | Jeff Boyer | Nick Cowell | Bob Foulk | Anderson | N/A | Andy Wiese | 39704-B Bobcat Bismarck BBF Finish Weld Cell (Priority 1) | Y | Y | [11 empty] | 2019-02-01 | New schedule as of 7/11. New Schedule as of 8-14. 11/15 working on punch list items for assembly
a1b0G00000CMRGmQAP | 2663 | Travis Pinkelman | Shane Halverson | Brad Bowhay | Anderson | PLC | Andy Wiese | Hillphoenix RIBS3 | Y | Y | [5 empty] | 2019-03-13 | 2019-03-20 | 2019-03-28 |  | 2019-04-01 | 2019-05-24 |  | New schedule being presented to customer at 1:00 on 1/15/19 | 2019-01-22
a1b0G00000CN4aWQAT | 2667 | Joseph Splichal | Robert Knox | Bob Foulk | Anderson | HMI | Dan Mitchell | CapStone Autoviri 5.2 - #21 thru #40 | W | Y |  |  |  |  | 40 - 1/18 41 - 1/25 42 - 2/1 43 - 2/8 44 - 2/15 45 - 2/22 46 - 3/1 47 - 3/8 48 - 3/15 49 - 3/22 | 36 & 37 1/4/19 38 & 39 1/18/19 40 & 41 2/1/19 42 & 43 2/15/19 44 & 45 3/1/19 46 & 47 3/15/19 48 & 49 3/29/19 | To follow completion of each cell | [5 empty] | Assembly is per cell Runoff dates are per 2 cells | 2019-01-21
a1b0G00000CMnfYQAT | 2668 | Joseph Splichal | Jake Crowley | Brad Bowhay |  |  | Andy Wiese | Lennox Return Bend Brazing System | Y | Y | Conveyor Mezzanine Bowl Feeders | Inspection Camera |  |  | 2019-02-08 | 2019-03-12 | 2019-03-20 | 2019-03-28 |  | 2019-04-01 | 2018-05-10 | 2018-06-07 | Two weeks on site at Acieta for addition of coils to the system. | 2019-01-21
a1b0G00000CNp5TQAT | 2670 | Steve Cooprider | Shane Halverson | Brad Bowhay |  |  | Dan Mitchell | Bobcat Gwinner Tube Weld & Case Half Assy | Y | Y |  |  |  |  | 2019-02-08 | 2019-02-22 |  | 2019-02-27 |  |  |  |  | Electrical assembly, and weld robot assembly/runoff. No programming at Acieta other than "strike an arc" on weld robots. | 2019-01-18
a1b0G00000CnyJVQAZ | 2671 | Steve Cooprider | Robert Knox | Darin Schneckloth |  | Oscar Gerry | Service, Andy Wiese | Bedford Plastics CNC Router and Saw | W | Y |  |  |  |  | 2019-02-15 | 2019-03-14 | 2019-03-20 | 2019-03-27 |  | 2019-04-01 | 2019-05-10 |  | behind a couple weeks, but might pull robot integration in early to offline program. | 2019-01-18
a1b0G00000CoxU8QAJ | 2672 | Jeff Boyer | Rusell Ridgway | Bob Foulk |  |  | Ryan Smallfoot | Eaton Belmond Grinder Load | N | W | 2019-01-25 | 2019-01-25 | 2019-03-01 | 2019-03-06 | 2019-03-22 | 2019-04-24 | 2019-04-25 | 2019-04-30 | N/A | 2019-05-01 | 2019-05-24 | 2019-06-30 | New Schedule (10/9/2018). 11/5/2018 - Schedule will need to be rebuild pending acceptable tray handling concept/direction. Schedule reloaded 12/10/2018. Schedule reloaded 1/21/19
a1b0G00000Cp0vWQAR | 2673 | Sammy Dowds |  | Bob Foulk |  |  | Service | Nascote (2516) Paint Line Equip Adder | W | Y | [11 empty] | 2019-01-21 | Need to be ordering parts by 10/4 | 2018-09-18
a1b0G00000CppN5QAJ | 2675 | Sammy Dowds |  | Bob Foulk |  |  | NA | John Deere Waterloo M900 Robot Replacement | W | W | [9 empty] | Robot 2: March 11 April/May TBD | Robot 2: March 16 April/May TBD |  | After on-site visit, John Deere would like to have one robot integrated before Jan. 02
a1b0G00000Cr4jZQAR | 2677 | Sammy Dowds |  | Bob Foulk |  |  | NA | Bobcat Wahp Grease Cyl Equip | W | Y | [11 empty] | 2019-01-25 | Panels have shipped, robots are on-site as well. Scope complete.
a1b0G00000Cr4YbQAJ | 2678 | Sammy Dowds |  | Bob Foulk |  |  | NA | Bobcat Wahp Tube Thread Panel | W | Y | [11 empty] | 2019-01-25 | Panel has shipped. Confirmed it is on-site.
a1b0G00000CzzugQAB | 2680 | Sammy Dowds |  | Darrin Schneckloth |  |  | Ryan Smallfoot | Superior Metal Spacer Plate LUL | Y | W |  |  |  |  | 2019-01-22 | 2019-02-25 | 2019-02-27 | 2/29/19 |  | 2019-03-04 | 2019-03-18 | 2019-04-04 | NEW Project, still need to validate dates - these are INITIAL ESTIMATES | 2018-10-10
a1b0G00000Czz6WQAR | 2681 | Jeff Boyer | Tim Bracha | Bob Foulk |  |  | Service | EMD 2060 Cell Mods | Y | W | 2019-01-25 | 2019-01-31 |  |  | 2019-03-31 | N/A | N/A | 2019-04-15 | N/A | September |  |  | Schedule will be loaded following 12-6 on site kickoff. Service pushed to Sept 2019
a1b0G00000D1EXA | 2683 | Travis Pinkelman, Sammy Dowds | Shane Halverson | Brad Bowhay |  |  |  | Cotterman RIBS/Weld System | N | W |  | 2019-01-25 | 2019-02-22 | 2019-03-01 | 2019-03-29 | 5/13/19-5/17/19 | 5/20/19-5/24/19 | 2019-05-30 |  | 2019-06-03 | 2019-08-09 |  | New schedule based off delay in getting ME release from customer and longer lead times on items | 2019-01-22
a1b0G00000D26zb | 2684 | Joseph Splichal | Jordan Wehmeier | Bob Foulk |  |  | Andy Wiese | Bobcat Gwinner Gen 6 Front Stamping Sub | N | W | 2019-01-22 | 2019-02-01 | 2019-02-08 | 2019-02-15 | 2019-03-08 | 2019-04-05 | 2019-04-09 | 2019-04-12 | NA | 2019-04-15 | 2019-05-10 | 2019-06-07 | Weld gun to ship 1/25 | 2019-01-21
a1b0G00000D1O8x | 2685 | Steve Cooprider | Tim Bracha | Bob Foulk |  | Oscar | Andy Wiese | Jacobs Corportation Machining System | W | Y |  |  | 2019-02-22 | 2029-02-01 | 2019-03-22 | 2019-04-23 | 2019-04-25 | 2019-05-01 |  | 2019-05-06 | 2019-05-31 |  |  | 2019-01-18 | [7 empty] | 209 | 23 | 17 | 3 | 1.5 | 26 | 8.5 | 0 | 90 | 0 | 40 | 219 | 23 | 17 | 5 | 1.5 | 26 | 13.5 | 3 | 90 | 0 | 40 | 153 | 5 | 0 | 0 | 1.5 | 0 | 13.5 | 3 | 90 | 0 | 40 | 72.2 | 12 | 22 | 1 | 0 | 36.7 | 0 | 0 | 0.5 | 0 | 0 | 0
a1b0G00000D1wER | 2686 | Joseph Splichal | Bryan Carsrud | Darrin Schneckloth |  |  | Dan Mitchell | Syngenta Bin Washing Complete | Y | W | 2018-12-21 | 2018-12-28 | 2019-02-01 | 2019-02-08 | 2019-03-15 | 2019-05-02 | 2019-05-09 | 2019-05-16 | NA | 2019-05-20 | 2019-07-05 | 2019-08-02 |  | 2019-01-21
a1b0G00000D2GGH | 2687 | Travis Pinkelman | Shane Halverson | Brad Bowhay |  |  |  | EM Dynamics RIBS System | N | Y | 2019-01-25 | 2019-02-08 | 2019-03-08 | 2019-03-15 | 2019-04-05 | 2019-06-04 | 2019-06-11 | 2019-06-20 |  | 2019-06-24 | 2019-08-30 |  | Presenting this schedule to customer at 9 am today | 2019-01-22
a1b0G00000D2DA2 | 2688 | Jeff Boyer | Rusell Ridgway | Bob Foulk |  |  |  | Bobcat Wahpeton Cylinder Assy Hardware | Y | Y | N/A |  | N/A | N/A | 2019-02-08 | N/A | N/A | 2019-02-08 | N/A | N/A | N/A | 2019-03-15 | Electrical design to be done in AutoCAD Electrical (Waived Requirement) Electrical released released 12-17-18
a1b0G00000D2yn4 | 2689 | Joseph Splichal | Rusell Ridgway | Bob Foulk |  |  |  | B&G Foods Line 23 Automation | W | N | 2019-01-18 | 2019-01-25 | 2019-02-15 | 2019-02-22 | 2019-03-22 | 2019-04-16 | 2019-04-18 | 2019-04-26 |  | 2019-04-29 | 2019-06-07 | 2019-07-05 |  | 2019-01-07
a1b0G00000D37j1 | 2690 | Jeff Boyer | Chris Bishop | Bob Foulk |  | O'Neil |  | NSK Washer Load | N | W | 2019-01-10 | 2019-01-17 | 2019-02-07 | 2019-02-14 | 2019-03-07 | 2019-04-18 | 2019-04-22 | 2019-04-25 |  | 2018-04-29 | 2019-05-17 | 2019-06-17 | New Schedule as of 11/20. Electrical released released 12-20-18
a1b0G00000D3J4i | 2691 | Sammy Dowds | Chris Bishop | Bob Foulk |  |  | Andy Wiese | Dixie Iron Works FastARC TT + Fixturing | N | W |  |  | 2019-02-15 | 2019-02-22 | 2019-03-15 | 2019-04-18 | 2019-04-23 | 2019-04-25 |  | 2019-04-30 | 2019-05-17 | 2019-05-24 | Awaiting work plans to re-work schedule
a1b0G00000D92fFQAR | 2692 | Joseph Splichal | [5 empty] | Bobcat Gwinner Gen6 ROPS Final Weld | Y | W | 2019-01-25 | 2019-02-01 | 2019-03-01 | 2019-03-08 | 2019-04-05 | 2019-05-28 | 2019-05-30 | 2019-06-06 |  | 2019-06-10 | 2019-07-12 | 2019-08-09 |  | 2019-01-21
a1b0G00000D1O8x | 2693 | Steve Cooprider |  | Brad Bowhay |  |  |  | Bobcat Gwinner Creaform Gauging | Y | W |  | 2019-01-25 | TBD Electrical Only |  | TBD Electrical Only |  |  | TBD Electrical Only |  |  |  |  | Mechanical already released. Need to work with Bobcat on Electrical panel needs. | 2019-01-18
a1b2I00000DHk0FQAT | 2695 | Jeff Boyer | Tim Bracha | Bob Foulk |  |  | Service | EMD Head Line Move (2032 Cell Relocation) | Y | W | 2019-01-18 | n/a | 2019-02-28 | n/a | 2019-03-28 | n/a | n/a | 2019-04-15 |  | May |  |  | new booking, team will review this project during 12/6 onsite meeting
a1b2I00000DJo1LQAT | 2696 | Sammy Dowds | [5 empty] | Bobcat Wahpeton Friction Weld LUL | Y | W | 2019-03-05 | 2019-03-12 | 2019-04-24 | 2019-05-03 | 2019-05-24 | 2019-06-17 | 2019-06-25 | 2019-06-28 |  | 2019-07-02 | 2019-08-02 | 2019-08-09 | Preliminary Schedule (Ideal) - no feedback on customer timeline yet
a1b2I00000DP8xgQAD | 2697 | Joseph Splichal | [5 empty] | Husky Studer Cell | Y | Y | 2019-03-01 | 2019-03-08 | 2019-03-30 | 2019-04-05 | 2019-05-07 | 2019-06-18 | 2019-06-25 | 2019-07-05 | N/A | 2019-07-08 | 2019-08-16 | 2019-09-13 |  | 2019-01-21
a1b2I00000DP9ETQA1 | 2698 | Joseph Splichal | [5 empty] | Husky Hardinge Cell | Y | Y | 2019-03-01 | 2019-03-08 | 2019-03-30 | 2019-04-05 | 2019-05-07 | 2019-06-18 | 2019-06-25 | 2019-07-05 | N/A | 2019-07-08 | 2019-08-16 | 2019-09-13 |  | 2019-01-21
a1b2I00000DPCuXQAX | 2699 | Jeff Boyer | Rusell Ridgway | Bob Foulk |  |  | Dan Mitchell | Gardner Denver Seat/Valve Machining | Y | Y | 2019-03-01 | 2019-03-08 | 2019-04-05 | 2019-04-12 | 2019-04-26 | 2019-06-14 | 2019-06-18 | 2019-06-21 |  | 2019-06-24 | 2019-08-02 | 2019-09-13 | New Schedule (1/22/2019)
a1b2I00000DQ2wOQAT | 2700 | Steve Cooprider | Shane Halverson | Brad Bowhay |  |  |  | Neapco Honda LM Gen2 | Y | Y | 2019-03-04 | 2019-03-08 | 2019-04-19 | 2019-04-26 | 2019-05-17 | 2019-06-06 | 2019-06-11 | 2019-06-13 |  | 2019-06-17 | 2019-06-28 |  |  | 2019-01-18
| FabTech | Rogers | Shane Halverson | Bob Foulk |  |  |  | Demo Bending Cell (FabTech) | Y | Y | [12 empty] | * Press is planned to ship to Acieta on 9-27-18 * Installation At FabTech 10/29/2018 to 11/05/2018 at 12pm * FabTech 11/05/2018 to 11/08/2018 at 4pm * Teardown at FabTech 11/08/2018 at 4pm to 11/09/2018 at 4pm * Shipment To Acieta 11/10/2018
| SRV-2500/2501 | Eric Johnson | Rusell Ridgway | Bob Foulk |  |  |  | 3M Brookings - APL2/3 & TP51 Update | Y | Y | [9 empty] | 2019-03-04 |  |  |  | 2019-01-03 | [7 empty] | 209 | 23 | 17 | 3 | 1.5 | 26 | 8.5 | 0 | 90 | 0 | 40 | 219 | 23 | 17 | 5 | 1.5 | 26 | 13.5 | 3 | 90 | 0 | 40 | 153 | 5 | 0 | 0 | 1.5 | 0 | 13.5 | 3 | 90 | 0 | 40 | 72.2 | 12 | 22 | 1 | 0 | 36.7 | 0 | 0 | 0.5 | 0 | 0 | 0

## Key (hidden)
Job # | PM | ME | EE | LB | RE | CE | Customer - Project | Total Sold Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Budget Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Backlog Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Cmptld Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Rework | Over budget | ME Release | EE Release | MFG Complete | Finishing Complete | ASSY Complete | Internal Runoff | Customer Runoff | Ship Date | Channel Partner Install Complete | Install Start | Install Complete | Comments | Last Updated | Mechanical Engineering Open Issues | Last Updated | Electrical Engineering Open Issues | Last Updated | Controls Status | Last Updated
Job # | PM Last Name | ME Last Name | EE Last Name | LB Last Name | RE Last Name | CE Last Name | Customer (First Line) Project Description (Second Line) | [46 empty] | Original Date Current Date Completed Date | Original Date Current Date | Original Date Current Date | Original Date Current Date | Original Date Current Date | Original Date Current Date | Original Date Current Date | Original Date Current Date | Original Date Current Date | Original Date Current Date | Original Date Current Date
2545 | Splichal | Halverson | Foulk |  |  |  | Spartan Mexico DCM 17 | [46 empty] | 2016-09-23 | 2016-09-30 | 2016-11-04 |  | 2016-12-30 | 2017-02-16 | 2017-02-21 | 2016-03-02 |  | 2016-03-06 | 2017-04-13 | * Pushing some duplicate parts into MFG already to reduce costs No mechanical release yet EE waiting on layout | 2016-09-19
[54 empty] | jhkljgkhvb | dsgaefgsefd
[54 empty] | kbk,b,mnb | sdgages
[54 empty] | Original Date | milestone date as of post kickoff dashboard
[54 empty] | Current Date | current milestone date
Red Date

## WK Conversion
Acieta Project Milestones Overview
1st Day of Current Year | 2015-01-01 | 209.4286
Updated: | 2019-01-22
|  |  | Sold Hours | [10 empty] | Target/Budgeted Hours | [10 empty] | Backlog Hours | [10 empty] | Completed hours | [11 empty] | Planned Completion Dates
Job Number | PM | Customer | Total Sold | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | CP | CS | Total Target | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | CP | CS | Total Back | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | CP | CS | Total Compl | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | CP | CS | Rework | Over budget | Mechanical Engineering Released | Electrical Engineering Released | Manufacturing Complete | Assembly Complete (Program Start) | Integration Finished (Ship) | Channel Partner Install Complete | Install Complete
Job # | PM | Customer Project | Total Sold Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Budget Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Backlog Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Total Actual Hrs | PM | ME | EE | Fab | Mach | Assy | Elect | Prog | Chan Install | Install | Rework | Over budget | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1907-04-08 | Steve Cooprider | Bobcat Gwinner Axle Cell | [46 empty] | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1906-11-09 | Greg Morehouse | New Hudson Facades Glass Loading Cells | 7767.7 | 983 | 1759 | 111.7 | 581 | 940 | 668 | 416 | 1189 | 0 | 1120 | 6667.7 | 983 | 759 | 111.7 | 581 | 940 | 668 | 416 | 1089 | 0 | 1120 | 5417 | 801 | 246 | 60 | 150 | 400 | 920 | 500 | 1120 | 0 | 1220 | 1171.11 | 182 | 843.5 | 57 | 15.17 | 25.7 | 0 | 0 | 46.24 | 0 | 1.5 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1907-03-11 | Steve Cooprider | Viking Pump Rotor L/UL | [46 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Acieta Calendar
2015
Green Days are Holidays
| January |  |  |  |  | February |  |  |  |  | March | [5 empty] | April |  |  |  |  | May |  |  |  |  | June
WK # | 1 | 2 | 3 | 4 | 5 | 5 | 6 | 7 | 8 | 9 | 9 | 10 | 11 | 12 | 13 | 14 | 14 | 15 | 16 | 17 | 18 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Mon |  | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 |  | 2 | 9 | 16 | 23 | 30 |  | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29
Tues |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30
Wed |  | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 |  | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24
Thu | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 26 |  | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30 |  | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25
Fri | 2 | 9 | 16 | 23 | 30 |  | 6 | 13 | 20 | 27 |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
Sat | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25 |  | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
Sun | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 |  | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 26 |  | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28
| July |  |  |  |  | August | [5 empty] | September |  |  |  |  | October |  |  |  |  | 1 2 3: November; 8 9 10 11 12 13 14: December
WK # | 27 | 28 | 29 | 30 | 31 | 31 | 32 | 33 | 34 | 35 | 36 | 36 | 37 | 38 | 39 | 40 | 40 | 41 | 42 | 43 | 44 | 44 | 45 | 46 | 47 | 48 | 49 | 49 | 50 | 51 | 52 | 1
Mon |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30 |  | 7 | 14 | 21 | 28
Tues |  | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 1 | 8 | 15 | 22 | 29
Wed | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30 |  | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25 |  | 2 | 9 | 16 | 23 | 30
Thu | 2 | 9 | 16 | 23 | 30 |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 26 |  | 3 | 10 | 17 | 24 | 31
Fri | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25 |  | 2 | 9 | 16 | 23 | 30 |  | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25
Sat | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 26 |  | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26
Sun | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30 |  | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 |  | 6 | 13 | 20 | 27
2016
Green Days are Holidays
| January |  |  |  |  | February |  |  |  |  | March |  |  |  |  | April |  |  |  |  | May | 1 2 3 4 5 6 7: June
WK # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 14 | 15 | 16 | 17 | 18 | 18 | 19 | 20 | 21 | 22 | 23 | 23 | 24 | 25 | 26 | 27
Mon |  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 |  | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25 |  | 2 | 9 | 16 | 23 | 30 |  | 6 | 13 | 20 | 27
Tues |  | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 |  | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 26 |  | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28
Wed |  | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 |  | 2 | 9 | 16 | 23 | 30 |  | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29
Thu |  | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 |  | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30
Fri | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24
Sat | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 |  | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30 |  | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25
Sun | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 26
| July | 1 2 3 4: August |  | September |  |  |  |  | October | [5 empty] | November |  |  |  |  | December
WK # | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 36 | 37 | 38 | 39 | 40 | 40 | 41 | 42 | 43 | 44 | 45 | 45 | 46 | 47 | 48 | 49 | 49 | 50 | 51 | 52 | 1
Mon |  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 26 |  | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26
Tues |  | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 |  | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 |  | 6 | 13 | 20 | 27
Wed |  | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30 |  | 7 | 14 | 21 | 28
Thu |  | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 |  | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 1 | 8 | 15 | 22 | 29
Fri | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30 |  | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25 |  | 2 | 9 | 16 | 23 | 30
Sat | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 |  | 1 | 8 | 15 | 22 | 29 |  | 5 | 12 | 19 | 26 |  | 3 | 10 | 17 | 24 | 31
Sun | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25 |  | 2 | 9 | 16 | 23 | 30 |  | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25